## VRP Public Record 01-01-2020
VRP ID # | Site Name | City/Town/ County | County | Site Address | Township Range | Latitude | Longitude | Size (acres) | Contamination Type | CERCLIS # | Applicant | NMED Project Manager | Application Received | Conditional Eligibility | Public Notice | Rejection | Final Eligibility | VRA signed | Final Work Plan Received | Final Work Plan Approved | Completion Report Received | Completion Report Approval | Certificate of Completion | Conditional Certificate of Completion | Termination | Land Use Restrictions | Institutional/ Engineering Controls | Covenant Not to Sue (CNS) | Transfer CNS | Recission | Status
53191002 | Angel Fire- LeBus | Angel Fire | Colfax | Intersection of Hwy 64 and Mountain View Blvd. | 1T, 25N, R15E, Sections 150, 167, 168 | 36.4305 | -105.2944 | 78.6 | creosote (PAHs) in groundwater, soil |  | Angel Fire, LLC | Muus | 2019-06-26
53191001 | 110 Gold Ave | Albuquerque | Bernalillo | 110 Gold Ave SE | T10N/R3E/Section 20 | 35.0826 | -106.6457 | 0.4 | TBD |  | KLG 30, LLC | Muus | 2019-04-24 | 2019-11-07 | 2019-12-01 | [15 empty] | Active
53191003 | Gallup Skate Park | Gallup | McKinley | 321 East Historic Highway 66 | T15N R18W S15 | 35.5295 | -108.7387 | 0.9 | Lead in subsurface soil |  | City of Gallup | Muus | 2019-10-16
53181004 | Galles Chevrolet | Albuquerque | Bernalillo | 1301-1601 Lomas Boulevard Northeast | T10N, R3E, Sec 16 | 35.0917 | -106.627 | 8.7 | Petroleum hydrocarbons, volatile organic compounds, semi-volatile organic compounds, and metals |  | Sandia Foundation | Richards | 2008-08-14 | 2018-10-03 | 2018-10-12 |  |  | 2018-12-06 | 2018-12-18 | 2019-01-04 | 2019-02-18 | 2019-04-05 | 2019-04-10 | [7 empty] | Closed
53181003 | Rueggli/Lift 1 Site | Taos Ski Valley | Taos | 5 Firehouse Road | T27N R14E, Sec 4 | see comments | see comments | 0.48 acres Rueggli, 0.10 acres Lift 1 site | VOCs and SVOCs typical of diesel fuel/degraded gasoline in soils |  | Taos Ski Valley | Muus | 2018-08-13 | 2018-10-29 | 2018-11-08 |  | 2019-01-24 | 2019-02-14 |  | 2019-01-24 | [10 empty] | Active
53181002 | Distribution Warehouse | Albuquerque | Bernalillo | 701 Comanche Road | T10N, R3E, Sec 4, NE 1/4 | 35.1255 | -106.625 | 8.7 | petroleum hydrocarbons; VOCs, heavy metals |  | GCB-1945, LLC | Muus | 2018-02-14 | 2018-05-04 | 2018-05-15 |  | 2018-07-11 | 2018-07-23 |  | 2018-11-09 | 2018-09-24 | 2018-11-09 | 2019-01-14 | [7 empty] | Closed
53181001 | 301 N. Main | Belen | Valencia | 301 N. Main |  | 34.6631 | -106.7765 | 0.5 | petroleum hydrocarbons in soil and groundwater |  | WSCI LLC | Cook | 2018-01-10 | [11 empty] | 2018-11-07 | [5 empty] | Closed
53171008 | Wirtco - 1 Hour Martinizing | Santa Fe | Santa Fe | 1091 S. St. Francis Drive | T17N, R9E, Sec 26 | 35.6746 | -105.9531 | 0.5 | Chlorinated solvents in ground water and soil vapor. |  | Wirtco Inc. | Richards | 2017-10-17 | 2017-12-01 | 2017-12-23 |  | 2018-02-27 | 2018-03-12 | 2018-10-22 | 2019-05-01 | [10 empty] | Active
53171007 | Arnie's Cleaners | Albuquerque | Bernalillo | 8217 Menaul Blvd. NE |  | 35.1095 | -106.5523 | 0.2066 | PCE, TCE, and daughters in soil vapor |  | Thu-Trang Nguyen | Cook | 2017-08-21 | 2017-12-15 | 2018-01-05 |  | 2018-03-28 | 2018-04-24 | 2018-03-30 | 2018-04-20 | [10 empty] | Active
53171006 | Mt. Chalchihuitl and Cerrillos Gravel Products | Cerrillos | Santa Fe | Cerrillos Hills Mining District | T14N, R8E, Sec 4,5,8 and T15N, R8E, Sec 33 | 35.4703 | -106.1125 | 678 | metals in soil, particularly antimony, arsenic, cadmium, copper, lead, thallium, and zinc |  | Santa Fe County | Muus | 2017-08-14 | 2017-10-16 | 2017-10-20 | [15 empty] | Active
53171005 | ProBuild Millworks Facility (former) | Albuquerque | Bernalillo | 6700 Bluewater Road |  | 35.0852 | -106.7143 | 7 | chlorinated solvents in subsurface soils, soil vapor, indoor air |  | ProBuild Real Estate Holdings, LLC | Muus | 2017-07-14 | 2017-10-04 | 2017-10-18 |  | 2017-12-21 | 2018-01-26 | 2018-03-28 | 2018-04-20 |  | 2018-10-23 | 2018-12-31 |  |  |  |  | 2019-03-11 |  |  | Closed
53171004 | Homewood Suites | Albuquerque | Bernalillo | 5400 San Antonio | T11N, R3E, Sec25 | 35.1588 | -106.5848 | 1.98 | Historic landfill |  | Mtn West Lodging | Cook | 2017-07-05 | 2017-10-06 | 2017-10-23 |  | 2018-01-30 | 2018-02-19 | 2017-09-06 | 2018-02-08 | [10 empty] | Active
53171003 | Legacy Hospitality Central | Albuquerque | Bernalillo | 222 Central Avenue SE | T10N, R3E, Sec 20 | 35.0833 | -106.645 | 0.814 | hydrocarbons in groundwater from offsite source |  | FBC II, LLC | Muus | 2017-05-03 | 2017-07-19 | 2017-07-28 |  | 2017-09-15 | 2018-01-04 |  | 2018-07-20 | 2018-06-07 | 2018-07-20 |  | 2018-09-24 |  |  |  | 2018-12-20 |  |  | Conditional Closure
53171002 | El Castillo Norte | Santa Fe | Santa Fe | 401 Old Taos Highway | T17N, R9E, Sec 24 | 35.6927 | -105.9733 | 2.52 | naphthalene compounds in soils |  | Presbyterian Church USA | Cook | 2017-04-14 | 2017-04-18 | 2017-06-19 |  | 2017-08-30 | 2017-09-16 | 2018-02-18 | 2018-04-02 | 2018-09-06 | 2018-09-10 | 2018-09-21 |  |  |  |  | 2018-11-14 |  |  | Closed
53171001 | Loving Salt | Malaga | Eddy | 1615 Pecos Highway (may be 1624 Pecos Highway) | T24S, R28E, Sec 19 | 32.2237 | -104.0729 | 2.38 | chloride and TDS |  | RK Pump & Supply | Muus | 2017-01-17 | 2018-01-16 | 2018-03-08 | 2018-09-06 | [14 empty] | Application denied
53161011 | College Plaza South - Unit 2404 | Santa Fe | Santa Fe | 2400 Cerrillos Road - Unit 2404 | T17N, R9E, Sec 34 | 35.6593 | -105.9806 | 6.48 | chlorinated solvents in soil vapor |  | B & LV College Plaza LP | Muus | 2016-11-04 | 2016-12-09 | 2016-12-25 |  | 2017-04-11 | 2017-04-28 | 2017-07-28 | 2017-09-15 | [10 empty] | Active
53161010 | 2917 Juan Tabo NE | Albuquerque | Bernalillo | 2917 Juan Tabo NE | T10N, R4E | 35.1157 | -106.5161 | 0.445 | chlorinated solvents in soil vapor |  | Russell K Whitener Irrovocable Trust | Cook | 2016-11-19 | [11 empty] | 2017-05-26 | [5 empty] | Closed
53161009 | Wellborn - DE Facility | Albuquerque | Bernalillo | 215 Rossmoor Road SW | T9N, R3E, Sec 36 | 35.0294 | -106.6603 | 61.15 | VOCs and heavy metals in soil and groundwater |  | Dunn Edwards Corporation | Richards | 2016-09-19 | 2016-09-20 | 2016-12-05 |  | 2017-01-26 | 2017-02-14 | 11/20/19 (Rec'd soil gas & indoor air work plan); 12/17/18 (Rec'd remediation work plan) | 12/21/18 (Approved soil gas & indoor air assessment work plan); 6/7/19 (Approved ground water remediation portion of work plan) | [10 empty] | Active
53161008 | 9220 Broadway SE | Albuquerque | Bernalillo | 9220 Broadway SE | T9N, R3E, Sec 31 | 34.9593 | -106.6597 | 9.7 | nitrate, chloride, sulfate in soil and groundwater |  | Storage Systems, LLC | Cook | 2016-08-19 | 2016-10-05 | 2016-10-27 |  | 2016-12-19 | 2017-01-10 | 2017-01-14 | 2017-01-20 | 2017-01-14 | 2017-01-26 | 2017-05-26 | [7 empty] | Closed
53161007 | Albuquerque Railyards | Albuquerque | Bernalillo | 1100 2nd Street SW (2nd and Commercial) | T10N, R3E, Sec 20, 29 | 35.0746 | -106.6501 | 27.32 | soil: metals, PAHs, petroleum hydrocarbos, LNAPL Soil vapor: VOCs groundwater: metals, naphthalenes; EDB buildings: ACM/LBP |  | City of Albuquerque | Richards | 2019-01-17 | 2019-03-05 | 2019-03-29 |  | 2019-05-25 | 2019-06-05 | 2019-06-28 | [11 empty] | Active
53161006 | Quality Pontiac Tract 1 | Albuquerque | Bernalillo | 1300 Lomas Blvd. NE | T10N, R3E, SE 1/4 Sec 16 | 35.091 | -106.629 | 4.974 | petroleum hydrocarbons in shallow soil |  | Sandia Foundation | Cook | 2016-06-30 | 2016-07-29 | 2016-09-09 |  | 2016-10-28 | 2016-12-09 | 2016-11-07 | 2017-01-27 | 2016-11-07 | 2017-01-27 | 2016-12-09 | [7 empty] | Closed
53161005 | A.C. Houston Lumber site | Gallup | McKinley | 104 North Second Street | T16N, R15W, Sec 18 | 35.5294 | -108.7425 | 6.8 | petroleum hydrocarbons, esp. BTEX and naphthalene in groundwater |  | AC Houston Lumber | Richards | 2016-05-13 | 2016-07-08 | 2016-08-22 |  | 2016-11-10 | 2016-12-05 | 2019-05-07 | 2019-05-25 | [10 empty] | Active
53161004 | Kmart Store #7017 | Roswell | Chaves | 1705 S. Main Street | T15N, R24E, Sec 9 | 33.3714 | -104.5215 | 4.98 | petroleum hydrocarbons and metals |  | Sears Holdings Management Corporation | Cook | 2016-05-02 | 2016-06-17 | 2016-07-12 |  | 2016-08-29 | 2016-09-14 | 2016-10-07 | 2016-11-14 | 2016-10-07 | 2016-11-14 | 2017-03-23 | [7 empty] | Closed
53161003 | Park Avenue Cleaners - SF | Santa Fe | Santa Fe | 720 St. Michaels Drive, Suite K | T17N, R9E, Sec 35 | 35.6577 | -105.9612 | 6.577 | PCE in sub-slab soils |  | Del Sol Shopping Center Partners | Muus | 2016-02-22 | 2016-03-25 | 2016-04-08 |  | 2016-06-03 | 2016-06-27 | 7/8/2016 11/19/2016 | 2016-07-25 | [10 empty] | Active
53161002 | Wagner Equipment | Albuquerque | Bernalillo | 4000 Osuna Road NE |  | 35.155 | -106.5967 | 25 | TPH-DRO, TPH-MRO in soils |  | Wagner Equipment Co | Richards | 2016-02-05 | 2016-03-24 | 2016-04-01 |  | 2016-06-03 | 2016-06-27 | 2016-07-07 | 2016-07-19 | [10 empty] | Active
53161001 | New Mexico Terminal Service (former Cal-Maine) | Albuquerque | Bernalillo | 9615 Broadway SE | T8N, R3E, Sec 6 | 34.9544 | -106.6688 | 65 | nitrate, TDS, chloride, sulfate in groundwater |  | KP Wildcat LLC | Richards | 2016-02-04 | 2016-05-02 | 2016-05-13 |  | 2016-09-13 | 2017-01-19 | 2017-06-06 | 2017-07-31 | [10 empty] | Active
53151004 | McAnally Enterprises (Las Cruces Community Farms) | Berino | Doña Ana | 415 San Benito Road | T26S, R3E, 1/4NW, 1/4SE | 32.0718 | -106.6215 | 250 | nitrate-N, chloride, sulfate, TDS in ground water. |  | Las Cruces Community Farms, LLC | Cook | 2015-08-27 | 2015-11-03 | 2015-11-13 |  | 2015-12-23 | 2016-01-29 | 2016-03-30 | 2016-06-10 | [10 empty] | Active
53151003 | Ritter Investments | Roswell | Chaves | 400 E. College Blvd. |  | 33.4085 | -104.5176 | 4.3 | BTEX, naphthalenes, arsenic, lead |  | Ritter Investments LLC | Richards | 2015-07-24 | 2016-02-15 | 2016-03-11 |  | 2016-05-02 | 2016-05-16 | 2019-08-29 | 2019-11-19 | [10 empty] | Active
53151002 | Piñon Square | Albuquerque | Bernalillo | 7849 Tramway Blvd NE |  | 35.1736 | -106.497 | 1 | PCE, TCE in soil and air |  | 7849 Tramway Blvd NE LLC | Richards | 2015-07-16 | 2015-11-03 | 2015-11-30 |  | 2016-01-29 | 2016-01-29 | 2016-04-07 | 2016-05-26 | [10 empty] | Active
53151001 | Marble-Arno Property | Albuquerque | Bernalillo | 830 Broadway Blvd NE |  | 35.0913 | -106.6424 | 2.1 | Residual TPH in soil; dissolved Fe and Mn in ground water. |  | City of Albuquerque | Cook | 2015-07-01 | 2015-07-29 | 2015-08-07 |  | 2015-11-17 | 2015-10-09 | 2015-09-22 | 2015-10-09 | 2016-04-18 | 2016-05-13 |  | 2016-05-24 |  | non-residential land use. |  |  |  |  | Active - CCOC
53141008 | Imperial Building (aka Hyder Property) | Albuquerque | Bernalillo | 205 Silver SW - Block 23, Lots 13 - 24, Original Townsite, Bernalillo County, NM | T10N,R3E, Sec 20 | 35.0826 | -106.6501 | 1.1 | chlorinated solvents and petroleum in soil vapor and soil |  | City of Albuquerque/UR 205 Silver, LLC | Muus | 2014-12-10 | 2015-01-13 | 2015-01-27 |  | 2016-08-04 | 2016-09-23 | 2016-01-28 | 2016-09-30 | 2016-01-15 | 2016-10-17 | 2016-11-04 | [7 empty] | closed
53141007 | 500 Copper Square Building | Albuquerque | Bernalillo | 500 Copper Ave NW |  | 35.0856 | -106.653 | 0.6 | Chlorinated solvents and petroleum in soil, soil vapor, and ground water |  | First Financial Credit Union | M. Hunter | 2014-10-29 | 2014-12-08 | 2014-12-19 |  | 2015-03-06 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2015-04-27 | 2015-07-01 | 2015-08-12 | [7 empty] | Closed
53141006 | Williams Property | Albuquerque | Bernalillo | 5101 Williams St SE |  | 35.0069 | -106.6598 | 28.5 | Nitrate, petroleum hydrocarbons |  | NMT Land Investments, LLC | Muus | 2014-10-17 | 2015-07-24 | 2015-08-07 |  | 2016-04-19 | 2016-08-10 | [12 empty] | Active
53141005 | Vehicle Maintenance Facility | Taos Ski Valley | Taos | 101 Ocean Blvd | T27N, R14E, Sec 4 | 36.5966 | -105.4596 | 0.54 | petroleum hydrocarbons in soils |  | Taos Ski Valley | Furmall | 2014-08-28 | 2014-09-26 | 2014-10-09 |  | 2014-12-03 | 2014-12-19 | 2014-08-28 | 2014-12-19 | 2015-02-06 | 2015-03-20 | 2015-05-15 | [7 empty] | Closed
53141004 | Wild Wings Subdivision Lot 2 | Farmington | San Juan | 2700 E. Main |  | 36.7416 | -108.1703 | 1.2 | petroleum hydrocarbons and one PCE detect in soil |  | Mavin Capital LLC & ITE Ltd. | Furmall | 2014-07-09 | 2014-07-24 | 2014-08-04 |  | 2014-09-12 | 2014-10-17 | NA | NA | NA | NA | 2014-10-17 |  |  |  |  | 2014-11-25 |  |  | Closed
53141003 | 8201 E Main St (former General Crude) | Farmington | San Juan | 8201 E Main St | T30N, R12W, Sec 21 | 36.7935 | -108.0967 | 12.45 | Petroleum hydrocarbons, esp. BTEX and naphthalene, PCE in soils; EDC, iron, manganese, boron in ground water |  | Desert Sun Investments, LLC | Muus | 2014-06-16 | 2014-08-12 | 2014-08-27 |  | 2014-10-31 | 2014-12-05 | 2015-01-27 | 2015-02-13 | [10 empty] | Active
53141002 | 247 Plaza Park | Las Vegas | San Miguel | 247 Plaza Park | T16N, R16E, Sec 27 | 35.5919 | -105.2271 | 0.1 | migrating petroleum hydrocarbon plume; benzo(a)pyrene above SSL |  | BRE-2, Inc. | Furmall | 2014-05-30 | 2014-07-18 | 2014-07-27 |  | 2014-09-09 | 2014-10-17 | 2014-10-13 | 2014-10-31 | 2014-10-13 | 2014-10-31 | 2014-11-18 |  |  |  |  | 2015-01-09 |  |  | Closed
53141001 | Elite Laundry | Gallup | McKinley | 208 E. Historic Hwy 66 | T15N, R18W, Sec 15 | 35.5287 | -108.7398 |  | Chlorinated solvents |  | Elite Laundry Co. | Cook | 2014-04-30 | 2014-06-13 | 2014-06-21 |  | 2014-09-09 | 2014-10-22 | 2014-10-02 | 2014-11-24 | [10 empty] | Active
53131004 | Plaza Maya | Albuquerque | Bernalillo | 615 First St. NW | T10N, R3E, Sec 17 | 35.0897 | -106.6471 | 1.27 | Petroleum hydrocarbons |  | SFGVI - NM, LLC | Richards | 2013-11-13 | 2013-12-30 |  |  | 2014-02-20 | 2014-02-24 | [12 empty] | Active
53131003 | Albuquerque First Baptist Church | Albuquerque | Bernalillo | 101 Broadway Blvd NE | T10N, R3E, Sec 20 | 35.0847 | -106.6457 | 6.96 | Petroleum hydrocarbons. |  | First Baptist Church | Furmall | 2013-11-01 | 2014-02-18 | 2014-02-28 |  | 2014-06-06 | 2014-06-06 | 2014-06-06 | 2014-06-18 | 2014-06-13 | 2014-06-19 | 2014-06-27 |  |  |  |  | 9-Jul-14 | 2015-12-11 |  | Closed
53131002 | Smith's #491 Fuel Center | Santa Fe | Santa Fe | 800 St. Michael's Drive | Santa Fe Grant | 35.6589 | -105.963 | 2.1 | TPH-DRO, TPH-ORO in soil |  | Smith's Food and Drug Stores | Furmall | 2013-09-04 | 2013-11-07 | 2014-01-10 |  | 2014-04-11 | 2014-05-02 | 2014-07-11 | 2014-07-21 | 2015-02-19 | 2015-03-06 | 2015-05-15 |  |  |  |  | 2015-09-25 |  |  | Closed
53131001 | Wyoming Mall | Albuquerque | Bernalillo | 2010 Wyoming Blvd NE |  | 35.1049 | -106.5503 | 6.01 | Chlorinated solvents. |  | Weingarten Realty Investors | Muus | 2013-07-02 | 2014-08-12 | 2014-08-27 |  | 2014-11-07 | 2014-12-03 | 9-Sep-13 27-Feb-14 5-Jul-14 | 2015-01-09 | 10-Dec-13 16-May-14 17-Nov-14 22-Dec-14 | 2015-01-09 |  | 2015-02-27 |  | non-residential land use; | maintain concrete slab |  |  |  | Active - CCOC
53121005 | Eagle Vista | Albuquerque | Bernalillo | E of Irving Blvd; W of Eagle Ranch Rd; S of The Aspens | T11N, R2E, Sec 7 | 35.1916 | -106.6644 | 6.771 | Chlorinated solvents, chromium. |  | Eagle Vista, LLC | Richards | 2012-09-17 | 2012-12-17 | 2012-12-28 |  | 2013-05-09 | 2013-05-13 | 18-Jun-2013; 15-Oct-18 | 20-Jun-13; 20-Nov-18 | 2013-09-05 | [9 empty] | Active
53121004 | 201 E. Coal Avenue | Gallup | McKinley | 201 E. Coal Avenue | T15N, R18W, Sec 15 | 35.5283 | -108.7398 | 0.5 | Chlorinated solvents in ground water and soil vapor. |  | Community Area Resource Enterprise, Inc. | Muus | 2012-07-09 | 2012-10-09 | 2012-10-23 |  | 2013-05-07 | 2013-05-14 | 2013-08-01 | 2013-08-01 | [10 empty] | Active
53121003 | Mast Voyager Tract | Albuquerque | Bernalillo | NWC of Transport ST SE and Sunport Blvd SE |  | 35.0495 | -106.6362 | 12.68 | Lead in soil, volatile organic compounds in ground water. |  | Thomas Macken | M. Hunter | 2012-03-13 | 2012-08-03 | 2012-08-14 |  | 2012-12-28 | 2013-01-22 | 2013-01-04 | 2013-01-28 | 2013-01-08 | 2013-02-21 | 2013-04-09 |  |  |  |  | 2014-03-28 |  |  | Closed
53121002 | Albuquerque Airpark Partners Property | Albuquerque | Bernalillo | 2901 Transport St SE and adjoining tract to south |  | 35.0526 | -106.6363 | 16.78 | Lead in soil, volatile organic compounds in ground water. |  | John Lorentzen | M. Hunter | 2012-03-13 | 2012-08-03 | 2012-08-13 |  | 2012-12-28 | 2013-01-22 | 2013-01-04 | 2013-01-28 | 2013-01-08 | 2013-02-21 | 2013-04-09 |  |  |  |  | 2014-03-28 |  |  | Closed
53121001 | 4102 Broadway SE | Albuquerque | Bernalillo | 4102,4110,4118,4126 El Rey SE | T9N, R3E, Sec 8 | 35.0191 | -106.644 | 15.37 | Nitrate, sulphate, total dissolved solids, chloride. |  | Albert Lemieux, Broadway LLC and Scott Whittington, El Rey Industrial LLC | Cook | 2011-09-23 | 2011-12-07 | 2011-12-01 |  | 2012-02-02 | 2012-04-13 | 2012-06-19 | 2012-08-14 | 2017-04-08 | 2017-08-11 |  | 2017-09-18 |  | non-residential land use |  | 2017-10-02 |  |  | Active - CCOC
53114001 | International Isotopes | Lea County | Lea |  | T18S, 36E, Sec 27 | 32.7186 | -103.3422 | 640 | Sulfate, chloride, TDS - trespassing ground water plume from Excel subsidiary. |  | Lea County | Muir | 2010-11-30 | 2011-04-26 | 2011-05-06 |  | 2011-06-17 | 2011-06-27 | 2011-06-30 |  | 2011-07-14 | 2011-07-21 | 2011-07-21 |  |  |  |  | 2011-12-08 |  |  | Closed
53112001 | Trinity Redevelopment | Los Alamos County | Los Alamos | 901 Trinity Drive |  | 35.8792 | -106.2944 | 15 | Various. |  | Los Alamos County | Cook | 2011-07-13 | [11 empty] | 2015-08-14 | [5 empty] | Closed
53103003 | Buena Vista Dairy (R-Qubed) | Mesquite | Doña Ana | 13085 Stern Drive | T25S, R3E, Sec 5 & 6 | 32.1597 | -106.6636 | 60.76 | Nitrate and dairy waste. |  | R-Qubed Energy, Inc. | Muus | 2010-05-18 | 2010-06-17 | 2010-07-01 |  | 2010-08-18 | 2010-09-22 | [6 empty] | 2018-12-24 | [5 empty] | closed-incomplete
53103002 | ASARCO Hop Canyon Site | Magdalena | Socorro | Former ASARCO Hop Canyon Site 1.2 miles S of Magdalena | T2S, R4W, Sec 34, 35 | 34.0929 | -107.2265 | 484.996 | Mining waste. |  | Asarco Multi-State Custodial Trust | Ehlert/Cook | 2010-04-05 | [17 empty] | Active
53103001 | Stanco Metal Products | Santa Teresa | Doña Ana | 301 Avenida de Ascencion | T29S, R2E, Sec 13 | 31.7885 | -106.6895 | 2.515 | Petroleum hydrocarbons in soil. |  | Verde Border One and Two LLC | Furmall | 2010-04-05 | 2010-08-19 |  |  | 2013-05-31 | 2013-06-06 | 2010-06-26 | 2010-08-10 | 2013-05-08 | 2013-06-28 | 2013-09-05 | [7 empty] | Closed
53102001 | Mills Plaza Shopping Center | Las Vegas | San Miguel | 254 Mills Avenue | T16N, R16E, Sec 22 | 35.6 | -105.2331 | 6.96 | PCE from dry cleaning. | NMD982555625 | Mills Acquisition Co. LLC | Muir | 2010-04-07 | 2010-07-22 | 2010-08-06 |  | 2010-10-08 | 2010-11-05 | 2010-10-26 |  | 2011-04-13 | 2011-10-28 | 2012-07-06 |  |  |  |  | 2014-01-10 |  |  | Closed
53101003 | Schwartzman Tract C-1-A-1-A | Albuquerque | Bernalillo | 3750 Prince Street | T9N, R3E, Sec 5 | 35.0312 | -106.6507 | 24.39 | Various. |  | BMR Funding LLC | Homer | 2010-04-16 | 2011-10-10 | 2011-11-17 |  | 2012-02-10 | 2012-03-01 | 2-May-12 2-Nov-12 | 14-May-12 6-Nov-12 | 2012-12-27 | 2013-01-22 | 2013-02-15 | [7 empty] | Closed
53101002 | US Postal Service Site | Albuquerque | Bernalillo | 3413 Broadway Blvd SE | T9N, R3E, Sec 5 | 35.0356 | -106.6479 | 42.8314 | Ground water contamination by creosote from off-site Superfund source. |  | US Food Service | Cook | 2010-02-16 | 2010-04-20 | 2010-05-28 |  | 2010-06-30 | 2010-08-02 |  |  | 2016-03-29 | 2016-04-08 | 2017-02-14 | [7 empty] | Closed
53101001 | 1501 12th St NW | Albuquerque | Bernalillo | 1501 12th St NW | T10N, R3E, Sec 18 | 35.1019 | -106.6584 | 1.47 | PCE in ground water. |  | Coe Properties | Furmall | 2009-11-18 | 2010-09-10 | 2011-02-19 |  | 2013-07-26 | 2013-08-23 | 2010-01-29 | 2013-07-26 | 2011-07-11 | 2013-09-18 | 2013-11-06 |  |  |  |  | 2014-02-21 |  |  | Closed
53094002 | Starlight Drive In Theatre | Roswell | Chaves | 1901 SE Main (US Hwy 285) | T11S, R24E, Sec 9 | 33.3683 | -104.5142 | 19.28 | Ground water contamination by PCE from off-site source. | EPA ill: NM0000605386 | Michael Shyne | Swanson | 2009-06-03 |  |  | 2011-04-25 | [14 empty] | Closed
53094001 | Hotel Clovis | Clovis | Curry | 201 N. Main Street | T2N, R36E, Sec 18 | 34.3998 | -103.2051 | 1.37 | Asbestos, lead paint, mold, pigeon droppings. |  | City of Clovis | Muir | 2008-12-15 | 2009-03-13 |  |  | 2010-04-05 | 2011-12-12 |  |  | 2010-03-08 | 2011-12-14 | 2011-12-23 | [7 empty] | Closed
53093001 | 1555 & 1565 West Picacho Avenue | Las Cruces | Doña Ana | 1555 & 1565 West Picacho Avenue | T23S, R1E, Sec 13 | 32.3119 | -106.7995 | 1.34 | Diesel and lead. |  | Russell Johnson | Muus | 2008-10-20 | 2009-03-06 | 2009-04-03 |  | 2009-07-10 | 2009-08-12 | 2009-02-09 |  | 2009-12-04 | 2009-12-04 |  | 2010-03-04 |  | Land use restricted to non-residential. | Concrete pad over contaminated soil. |  |  |  | Active - CCOC
53092001 | Santa Fe County Judicial Complex | Santa Fe | Santa Fe | 327 Sandoval St | Land Grants, Civil Colonies | 35.6849 | -105.9434 | 2.35 | Petroleum hydrocarbons in soil and ground water. |  | Santa Fe County | Richards | 2009-04-29 | 2010-08-06 | 2010-08-25 |  | 2014-05-09 | 2014-07-14 | 2015-02-16 | 2015-02-23 | 2015-09-23 | 2016-02-19 |  | 2016-02-26 | [6 empty] | Active - CCOC
53091002 | WESST Enterprise Center | Albuquerque | Bernalillo | 205 Roma Ave NE | T10N, R3E, Sec 17 | 35.0885 | -106.6443 | 0.4425 | Ground water contamination by PCE from off-site source. |  | WESST Corporation | Muir | 2009-10-07 | 2009-12-04 | 2010-12-21 |  | 2010-05-05 | 2010-05-18 | 2010-11-24 |  | 2011-04-11 | 2011-11-09 | 2012-06-26 |  |  |  |  | 2013-06-03 |  |  | Closed
53091001 | North I-25 Corp Center aka Philips Site | Albuquerque | Bernalillo | 9201 Pan American Freeway NE | T11N, R3E, Sec 12 | 35.191 | -106.5848 | 59.662 | Historic landfill, chlorinated solvents. |  | Reid and Associates, LLC | Cook | 2008-11-25 | 2009-04-10 |  |  | 2009-12-28 | 2-Aug-10 3-May-17 |  |  | 2017-07-10 | 2018-02-05 |  | 2019-07-08 |  |  | Vapor mitigations system in easement |  |  |  | Active
53085003 | San Juan Spring Co. East | Farmington | San Juan | 409 E. Broadway St. | T29N, R13W, Sec 15 | 36.7282 | -108.201 | 1.29 | Dissolved chromium in ground water and petroleum hydrocarbons in soil. |  | San Juan Spring Co. | Homer | 2008-01-10 |  |  | 2014-08-29 | [14 empty] | Closed
53085001 | SAMCO Associates | Socorro | Socorro | 915 N. California Street | T22S, R3E, Sec6 | 34.0681 | -106.8933 | 0.364 | Petroleum hydrocarbons. |  | SAMCO Associates/David Boggs | Muir | 2008-09-23 | 2008-05-06 | 2008-05-31 |  | 2008-09-23 | 2008-11-07 |  |  | 2009-02-05 | 2009-04-21 | 2009-05-08 |  |  |  |  | 2009-06-23 |  |  | Closed
53083003 | Sun Valley Do it Center | Silver City | Grant | 1401 Silver Heights Boulevard | T17S, R14W, Sec 34 | 32.7802 | -108.2746 | 1.13 | Chlorinated hydrocarbon contamination in the subsurface soil, specifically PCE. |  | Mr. Roy and Mrs. Mary Chavez | Muir | 2008-04-23 | 2008-06-03 | 2008-06-19 |  | 2008-07-17 | 2008-08-11 |  |  | 2008-07-07 | 2008-07-25 | 2008-07-24 |  |  |  |  | 2008-07-24 |  |  | Closed
53083002 | Tyrone Gun Club | Tyrone | Grant | Approx. 1 mile west of Tyrone | T18S, R14W, Sec 29 | 32.7167 | -108.3135 | 16.52 | Lead - firing range. |  | New Mexico State Land Office | Furmall | 2007-12-05 | 2008-05-05 | 2008-05-28 |  | 2008-09-23 | 2008-12-03 | 2008-09-23 | 2013-05-09 | 2013-07-17 | 2013-10-21 | 2013-11-06 | [7 empty] | Closed
53083001 | Inspiration Heights | Las Cruces | Doña Ana | 7805 Arroyo Avenue | T22S, R3E, Sec 6 | 32.4177 | -106.6826 | 135 | Petroleum hydrocarbons and total nitrates in soil and ground water. |  | Pacific Holt Corporation | Muir | 2004-06-22 | 2008-05-06 |  |  | 2008-11-20 | 2009-01-28 |  |  | 2007-09-17 | 2009-04-13 | 2009-04-15 |  |  |  |  | 2009-05-19 |  |  | Closed
53081007 | Casa Chevrolet | Albuquerque | Bernalillo | 7201 Lomas Blvd. | T10N, R4E, Sec 18 | 35.0875 | -106.567 | 6.5609 | Petroleum hydrocarbons. |  | Group 1 Automotive, Inc. | Muir | 2008-09-29 | 2008-12-29 |  |  | 2009-05-08 | 2009-05-14 |  |  | 2009-07-01 | 2009-08-03 | 2009-08-21 | [7 empty] | Closed
53081006 | Downtown @ 700-2nd | Albuquerque | Bernalillo | 700 2nd NW | T10N, R3E, Sec 17 | 35.0904 | -106.6478 | 0.729 | Petroleum hydrocarbons, chlorinated solvents. |  | Supportive Housing Coalition of New Mexico | Muir | 2008-08-13 | 2008-09-15 | 2008-10-14 |  | 2008-10-17 | 2008-10-28 | 2008-10-29 |  |  | 2008-10-29 | 2008-10-31 |  |  |  |  | 31-Oct-08 | 2008-12-18 |  | Closed
53081005 | Albuquerque Locomotive Shops (formerly BNSF-CWE) | Albuquerque | Bernalillo | 2nd & Bridge Sts | T10N, R3E, Sec 29 | 35.07 | -106.65 | 28 | Petroleum hydrocarbons, metals, asbestos. |  | City of Albuquerque | Furmall | 2008-07-11 | [17 empty] | Closed
53081004 | Holiday Park Cleaners | Albuquerque | Bernalillo | 2917 Juan Tabo NE | T10N, R4E, Sec 9 | 35.1151 | -106.5158 | 5 | Tetrachloroethene (PCE) in soil. |  | William and Glenda Quint | Muir | 2008-05-09 | 2008-08-01 | 2008-09-23 |  | 2008-11-21 | 2008-12-23 |  |  | 2008-12-15 | 2009-01-13 | 2009-01-14 | [7 empty] | Closed
53081003 | Truly Nolen Exterminating | Albuquerque | Bernalillo | 510 Candelaria Rd. NE | T10N, R3E, Sec 9 | 35.1161 | -106.6343 | 2 | Chlordane and heptaclor. |  | Jaynes Corporation | Muir | 2008-06-18 | 2008-11-10 |  |  | 2009-01-14 | 2009-02-03 |  |  |  | 2009-02-19 | 2009-02-26 |  |  |  |  | 2009-04-06 |  |  | Closed
53081002 | Oakland Avenue Landfill | Albuquerque | Bernalillo | 6114 Oakland Avenue NE | T11N, R3E, Sec 13 | 35.1859 | -106.5758 | 17.39 | Muncipal solid waste. |  | Vandy Investments, Inc. | Muir | 2008-03-21 | 2008-05-13 |  |  | 2008-12-23 | 2009-02-04 |  |  |  | 2009-04-30 | 2009-06-23 |  |  |  |  | 2009-07-25 |  |  | Closed
53081001 | Duke City Distributing | Albuquerque | Bernalillo | 3203 Broadway SE | T10N, R3E, Sec 32 | 35.0467 | -106.6471 | 1.7235 | Petroleum hydrocorbons and heavy metals in soil and ground water. |  | Duke City Distributing, Lo. Inc. | Shean | 2007-11-13 |  |  |  | 2008-06-03 | [5 empty] | 2008-07-02 |  |  |  |  | 17-Jul-08 |  |  | Closed
53072001 | Phillips Petroleum | Santa Fe | Santa Fe | 760 Cerrillos Road | T17N, R9E, Sec 26 | 35.6792 | -105.9509 | 0.39946 | Petroleum hydrocarbons in soil and groundwater; pce contamination in groundwater. |  | City of Santa Fe | Brooks | 2007-04-03 |  |  |  | 2007-08-21 | [5 empty] | 2009-12-18 | [7 empty] | Closed
53071002 | Fina Truck Stop - Parcel "A" | Albuquerque | Bernalillo | 1901 Menual Blvd. NE | T10N, R3E, Sec 9 | 35.1092 | -106.6248 | 3.6 | Petroleum hydrocarbon from transgressing plume. |  | John Paloni | Shean | 2006-02-07 |  |  |  | 2007-04-12 | [5 empty] | 2007-08-16 | [7 empty] | Closed
53071001 | Fina Truck Stop - Parcel "B" | Albuquerque | Bernalillo | 1901 Menual Blvd. NE | T10N, R3E, Sec 9 | 35.1092 | -106.6248 | 3.6 | Petroleum hydrocarbons in soil and ground water. |  | John Paloni | Muus | 2006-12-01 | 2007-03-09 | 2007-03-07 |  | 2007-04-12 | 2007-05-01 | [5 empty] | 2008-04-15 |  |  | Continue remediation under the oversight of the Petroleum Storage Tank Bureau. |  |  |  | Active - CCOC
53065001 | Belen National Guard Armory J | Belen | Valencia | 715 South Main Street | T7N, R2E, Sec 20 | 34.6538 | -106.7794 | 4.5 | Iron and manganese in ground water. |  | NM Department of Military Affairs | Muir | 2006-04-20 |  |  | 2009-12-31 | [14 empty] | Closed
53063001 | White Sands Boulevard | Alamogordo | Otero | All at SEC of 10th Street and White Sands Boulevard | T16S, R10E, Sec 19 | 32.8996 | -105.9601 | 4.85 | Petroleum hydrocarbons in soil and ground water, and chlorinated solvents in groundwater. | NM000605693 | CAP II 10th/White Sands, LLC | Richards | 2006-01-23 |  |  |  | 2006-06-16 | [6 empty] | 9-Feb-2007 29-Dec-08 revised |  |  | Continued monitoring of ground water. | 21-Mar-07 29-Dec-08 revised 25-Sep-09 revised |  |  | Active - CCOC
53062001 | Premier Nissan | Santa Fe | Santa Fe | 2005 St. Michael's Drive | T17N, R9E, Sec 34 | 35.6596 | -105.9663 | 2.9 | Petroleum hydrocarbons associated with hydraulic lifts and sump. |  | Omega Automotive Real Estate, LLC | Bynum | 2006-04-06 |  |  |  | 2006-05-31 | [5 empty] | 2006-06-02 |  |  |  |  | 2006-06-02 | 2010-10-22 |  | Closed
53061007 | Schwartzman Tract 15 | Albuquerque | Bernalillo | 3301 Second St. SW | T9N, R3E, Sec 5 | 35.0392 | -106.6565 | 45.5 | Petroleum hydrocarbons, creosote, iron and manganese, chlorinated solvents, PCBs, pesticides. |  | Schwartzman, Inc | Muir | 2006-06-15 |  |  | 2009-12-23 | [14 empty] | Closed
53061006 | Storage Systems, LLC | Albuquerque | Bernalillo | Lots 30, 31 and 32 Block 4 of Tract A Unit B of N. Albuquerque Acres | T11N, R3E, Sec 12 | 35.1951 | -106.5856 | 2.45 | Municipal solid waste. |  | Storage Systems, LLC | Bascomb | 2006-06-13 |  |  |  | 2007-02-19 | [5 empty] | 2008-04-15 |  |  |  |  | 2008-06-20 | 2016-05-06 |  | Closed
53061005 | Broadway and Murray Site | Albuquerque | Bernalillo | 6501 Broadway Blvd SE | T9N, R3E, Sec 17 | 35.0043 | -106.6538 | 36.9707 | Nitrate in soils and ground water. |  | Anthony E. Giraudo and Patricia A. Giraudo | Cook | 2006-04-19 | 2006-06-10 |  |  | 2006-07-20 | 2006-08-25 | 2006-09-13 |  |  | 2006-09-13 |  | 2006-09-14 |  |  | Deed restriction, site drainage structures. | 2006-10-27 |  |  | Active - CCOC
53061004 | Price's Valley Gold North Dairy - North Area | Rio Rancho | Sandoval | 618 Highway 528 | T13N, R3E, Sec 25 | 35.3194 | -106.5742 | 86.2 | Nitrogen compounds in soil. |  | Valley Gold Farms | Bascomb | 2005-11-21 | 2006-03-22 |  |  | 2006-06-28 | 2006-07-12 | 2006-07-11 | 2006-07-28 |  | 2006-09-25 | 2006-11-28 |  |  |  |  | 16-Mar-07 17-Jan-08 9-Apr-08 2-Feb-14 | 30-Nov-10 27-Dec-11 |  | Closed
53061003 | Americus Mechenbier | Bernalillo County | Bernalillo | SE Corner of San Mateo Blvd and Venice Ave | T11N, R3E, Sec 12 | 35.196 | -106.5863 | 6.04 | Muncipal solid waste. |  | Americus L.L.C. | Shean | 2005-08-04 |  |  |  | 2007-02-09 |  |  |  | 2009-08-03 |  | 2009-08-03 |  |  |  |  | 2009-08-05 |  |  | Closed
53052001 | AT&SF Tie Treating Plant - Las Vegas | Las Vegas | San Miguel | Grand Avenue | T16N, R16E, Sec 26 | 35.5786 | -105.2158 | 20 | Zinc chloride. |  | BNSF Railway Company | Muir | 2006-03-02 | 2005-10-20 |  |  | 2006-03-08 | 2006-04-28 | 2008-09-17 |  | 2008-05-25 | 2009-05-18 | 2009-05-18 | [7 empty] | Closed
53051006 | Eubank Landfill - Northeast Fill Area | Albuquerque | Bernalillo | Located at south end of Eubank Ave SE | T10N, R4E, Sec 33 | 35.0541 | -106.5221 | 40 | Lead, volatile and semi-volatile organic compounds. |  | NM State Land Office | Shean | 2004-10-18 |  |  |  | 2005-04-06 | [5 empty] | 2005-07-07 | [7 empty] | Closed
53051003 | Hyder Property | Albuquerque | Bernalillo | Block 23, Lots 13 - 24, Original Townsite, Bernalillo County, NM | T10N,R3E, Sec 20 | 35.0826 | -106.6501 | 1 | Potential lead contaminated surface soils, volatile and semi-volatile organic compounds in subsurface. |  | City of Albuquerque | Shean | 2004-11-09 |  |  |  | 2005-03-22 | [5 empty] | 2005-05-27 | [7 empty] | Closed
53051002 | Ponderosa Products - Lots 1 and 2 | Albuquerque | Bernalillo | 1701 Bellamah Ave | T10N,R3E, Sec 7 | 35.1045 | -106.6631 | 7.48 | Petroleum hydrocarbons, formaldehyde. |  | Saw Mill Community Land Trust | Shean | 2004-10-19 |  |  |  | 2005-05-06 | [5 empty] | 2009-09-22 |  |  |  |  | 2009-12-28 |  |  | Closed
53051001 | Schwartzman Tract 14S | Bernalillo County | Bernalillo | NE corner of 2nd Street & Rio Bravo Blvd | T9N, R3E, Sec 5 | 35.0281 | -106.6566 | 30.8045 | Petroleum hydrocarbons, chlorinated solvents, creosote. |  | Schwartzman, Inc | Bascomb | 2004-07-19 |  |  |  | 2005-09-29 | [5 empty] | 2007-03-09 |  |  |  |  | 2007-03-09 |  |  | Closed
53051001 | Schwartzman Tract 16 | Bernalillo County | Bernalillo | E of Barr Canal/W.of Albu. Riverside Drain | T10N, R3E, Sec 31 | 35.0445 | -106.661 | 126.47 | Petroleum hydrocarbons, chlorinated solvents, creosote, nitrate. |  | Schwartzman, Inc | Bascomb | 2004-07-19 |  |  |  | 2005-09-29 | [5 empty] | 2007-06-27 |  |  |  |  | 2008-05-06 |  |  | Closed
53051001 | Schwartzman Tract 17 | Albuquerque | Bernalillo | W. of 2nd Street/appx. 750 ft S. Woodward RD | T10N, R3E, Sec 32 | 35.0479 | -106.656 | 6.92 | Petroleum hydrocarbons, chlorinated solvents, creosote. |  | Schwartzman, Inc | Bascomb | 2004-07-19 |  |  |  | 2005-09-29 | [5 empty] | 2007-04-13 |  |  |  |  | 2007-04-13 |  |  | Closed
53051001 | Schwartzman Tract 28 | Bernalillo County | Bernalillo | W. of I-25/N.of Tract4 | T9N, R3E, Sec 5 | 35.0413 | -106.6401 | 1.87 | Petroleum hydrocarbons, chlorinated solvents, creosote. |  | Schwartzman, Inc | Bascomb | 2004-07-19 |  |  |  | 2005-09-29 | [5 empty] | 2007-03-09 |  |  |  |  | 2007-03-09 |  |  | Closed
53051001 | Schwartzman Tract 5 | Bernalillo County | Bernalillo | E. of Broadway/appx 1,125 ft N. of Rio Bravo | T9N, R3E, Sec 5, 8 | 35.0343 | -106.6453 | 13.71 | Petroleum hydrocarbons, chlorinated solvents, creosote. |  | Schwartzman, Inc | Bascomb | 2004-07-19 |  |  |  | 2005-09-29 | [5 empty] | 2007-03-09 |  |  |  |  | 2007-03-09 |  |  | Closed
53051001 | Schwartzman Tract B | Bernalillo County | Bernalillo | NW of Prince Rd and Rio Bravo Blvd | T9N, R3E, Sec 5 | 35.0293 | -106.6536 | 26.173 | Petroleum hydrocarbons, chlorinated solvents, creosote. |  | Schwartzman, Inc | Bascomb | 2004-07-19 |  |  |  | 2005-09-29 | [5 empty] | 2007-03-28 |  |  |  |  | 2007-05-21 |  |  | Closed
53051001 | Schwartzman Tract C-2-A | Bernalillo County | Bernalillo | 500ft from NW corner Rio Bravo/Broadway | T9N, R3E, Sec 8 | 35.029 | -106.6508 | 31.191 | Petroleum hydrocarbons, chlorinated solvents, creosote. |  | Schwartzman, Inc | Bascomb | 2004-07-19 |  |  |  | 2005-09-29 | [5 empty] | 2007-03-30 |  |  |  |  | 2007-03-30 |  |  | Closed
53051001 | Schwartzman Tract C-3-A | Bernalillo County | Bernalillo | NE of Prince Rd and Rio Bravo Blvd | T9N, R3E, Sec 8 | 35.0273 | -106.6519 | 3.1764 | Petroleum hydrocarbons, chlorinated solvents, creosote. |  | Schwartzman, Inc | Bascomb | 2004-07-19 |  |  |  | 2005-09-29 | [5 empty] | 2007-03-28 |  |  |  |  | 2007-05-21 |  |  | Closed
53044003 | Gnome-Coach | Carlsbad | Eddy | 25 miles east of Carlsbad, Eddy County, New Mexico | T23S, R30E, Sec 31 | 32.263 | -103.867 | 680 | Radiological / diesel contamination of surface soils. | NM8890116132 | DOE Legacy Management | Richards | 2004-05-12 | 2004-07-15 | 2004-08-25 |  | 2004-10-08 | 2005-06-22 |  |  | 2005-12-21 | 2006-01-27 |  | 2014-09-25 |  | Ranching. | Maintain cap over shaft and drilling exclusion within 40 ft. No drilling/excavating anywhere onsite below 20 ft. Signage around perimeter and at road crossings. |  |  |  | Active - CCOC
53044002 | CAP XXX - Main & McGaffey [Former Safeway] | Roswell | Chaves | 1200 South Main Street | T11S, R24E, Sec 9 | 33.3796 | -104.5232 | 2.04 | Petroleum hydrocarbons and PCE associated with transgressing plumes. |  | CAP II – Main/McGaffey, LLC | Shean | 2003-10-09 |  |  |  | 2004-01-07 | [5 empty] | 2004-07-06 |  |  |  |  | 2004-07-12 | 2014-09-30 |  | Closed
53044001 | Tastee Freez, Roswell | Roswell | Chaves | 1303 W. Second St. | T10S, R24E, Sec 32 | 33.3947 | -104.54 | 0.89 | PCE, TCE. |  | Mr. and Mrs. Owen & Mrs Angelos | Bascomb | 2003-08-29 |  |  |  | 2003-12-03 | [5 empty] | 2005-04-25 |  |  |  |  | 2005-04-25 |  |  | Closed
53043001 | ASARCO Deming Mill [Windblown Tailings] | Deming | Luna | County Road 394, circa one mile NW of Deming | T23S, R9W, Sec 20,21,29 | 32.2925 | -107.7827 | 54.43 | Lead and heavy metals. | NMMMD LU009RE | Asarco Incorporated | Muus | 2004-06-22 | 2004-07-16 | 2004-09-09 |  | 2004-10-20 | 2004-12-10 | 2007-09-11 | 2008-12-23 | 2009-05-04 | 2013-10-21 |  | 2014-01-07 |  | Non-residential use due to As. | Restrictive covenant to restrict land use to non-residential. | 2014-06-13 |  |  | Active - CCOC
53042001 | Gasbuggy | Rio Arriba County | Rio Arriba | Appx. 25 miles from Dulce, NM in the Carson National Forest | T29N, R4W, Sec 36 | 36.6779 | -107.209 | 20 | Petroleum hydrocabons (diesel in drilling mud). |  | DOE Legacy Management | Richards | 2004-04-27 | 2006-08-02 |  |  | 2008-09-26 | [13 empty] | Active
53041006 | CAP II - G and G Auto | Farmington | San Juan | 701 East 20th Street | T29N, R13W, Sec 10 | 36.7482 | -108.1969 | 3.26 | Petroleum hydrocarbons. |  | CAP II - 20th/Butler, LLC | Muus | 2004-06-28 | 2004-07-20 | 2004-08-20 |  | 2004-09-24 | 2004-10-05 |  |  | 2004-10-08 | 2004-10-25 |  | 2004-11-12 |  |  | PSTB Quarterly Monitoring Reports provided to VRP. | 2004-11-12 | 2014-12-05 |  | Conditional closure/Active - CCOC
53041005 | Sandia Battery | Bernalillo | Sandoval | Tract 5, Bernalillo Industrial Subdivision | T12N, R4E, Sec 7 | 35.2931 | -106.5558 | 2 | Lead. | NM0001899913 | Bernalillo Development Corporation | Richards | 2004-06-02 | 2005-05-19 | 2011-02-10 |  | 2006-03-22 | 2006-04-12 | 2009-08-26 | 2010-08-18 | 2014-02-14 | 2014-06-20 |  | 2014-06-27 |  | land use restricted to industrial/commercial | asphalt cap, concrete gutters, retention pond |  |  |  | Active - CCOC
53041004 | Thriftway- Wright Gallery | Albuquerque | Bernalillo | 2130, 2104, 2108 San Mateo Blvd | T10N, R3E, Sec 13 | 35.1013 | -106.5861 | 0.32 | Petroleum hydrocarbons. |  | Thriftway Marketing, Corp. | Bascomb | 2004-05-14 |  |  |  | 2005-02-02 | [5 empty] | 2005-08-18 |  |  |  |  | 2005-08-18 |  |  | Closed
53041003 | Caldwell Motors | Valencia County | Valencia | 322 North Main Street | T5N,R2E, Sec 15 | 34.6637 | -106.7752 | 0.37 | Petroleum hydorcarbons and heavy metals in soils. |  | Wells Fargo Bank New Mexico | Mariano | 2003-11-04 |  |  |  | 2004-05-20 | [5 empty] | 2007-03-09 |  |  |  |  | 2008-03-07 |  |  | Closed
53041002 | CAP XXX- Main & Reinken [McCasland Chevrolet] | Belen | Valencia | 315 North Main Street | T5N, R2E, Sec 18 | 34.663 | -106.7763 | 1.8 | Petroleum hydrocarbons. |  | CAP XXX - Main/Reinken, LLC | Muus | 2003-10-09 | 2003-11-07 | 2003-11-19 |  | 2004-01-07 | 2004-04-21 |  |  | 2004-04-30 | 2004-06-29 |  | 2004-07-12 |  |  | PSTB Quarterly Monitoring Reports provided to VRP. | 2004-07-12 |  |  | Conditional closure/Active - CCOC
53041001 | Schwartzman Inc, Tract 1 | Bernalillo | Bernalillo | Rio Bravo & I-25 | T9N, R3E, Sec 8 & 9 | 35.0229 | -106.6432 | 51.76 | Petroleum hydrocarbons. |  | Schwartzan, Inc. | Bascomb | 2003-08-18 |  |  |  | 2003-10-31 | [5 empty] | 2003-11-21 |  |  |  |  | 26-Nov-03 13-Jun-08 |  |  | Closed
53041001 | Schwartzman Inc, Tract 2 | Bernalillo | Bernalillo | Rio Bravo & Broadway | T9N, R3E, Sec 8 & 9 | 35.0234 | -106.6471 | 8.3 | Petroleum hydrocarbons. |  | Schwartzan, Inc. | Bascomb | 2003-08-18 |  |  |  | 2003-10-31 | [5 empty] | 2003-11-21 |  |  |  |  | 26-Nov-03 4-Jun-08 |  |  | Closed
53034001 | Awtrey Enterprises | Clovis | Curry | 965A Humphrey Road | T2N, R36E, Sec 15 | 34.397 | -103.156 | 15 | Petroleum hydrocarbons. |  | Brett Johnson (505 Resources) | Mariano | 2002-12-19 |  |  |  | 2003-05-12 | [5 empty] | 2004-09-12 | [7 empty] | Closed
53032001 | Santa Fe Rail Yard Properties | Santa Fe | Santa Fe | Santa Fe Rail Yard | T17N, R9E, Sec 23 | 35.6799 | -105.9503 | 49 | Metals & petroleum hydrocarbons in soil. |  | City of Santa Fe | Mariano | 2003-02-01 |  |  |  | 2003-10-03 | [5 empty] | 2006-02-27 |  |  |  |  | 2006-03-31 |  |  | Closed
53031007 | Bell Trading Post property | Albuquerque | Bernalillo | 1503 Central Ave | T10N, R3E, Sec 18 | 35.0905 | -106.6644 | 1 | Lead in soils, asbestos. |  | City of Albuquerque | Shean | 2003-06-26 |  |  |  | 2003-12-23 | [5 empty] | 2005-11-14 |  |  |  |  | 2005-11-14 |  |  | Closed
53031006 | Palo, Verde, Ltd. Belen | Belen | Valencia | 1304 South Main Street | T5N, R2E, Sec 19 | 34.6414 | -106.7803 | 6.3007 | Petroleum hydrocarbons. |  | Palo Verde, Ltd. | Shean | 2003-04-22 |  |  |  | 2003-06-05 | [5 empty] | 2003-08-06 |  |  |  |  | 2003-08-15 |  |  | Closed
53031005 | Capital Recycling | Albuquerque | Bernalillo | 2330 Second Street SW | T10N, R3E, Sec 29 | 35.0608 | -106.6529 | 2.13 | Petroleum hydrocarbons, asbestos. |  | BNSF Railway Co. | Muus | 2002-12-18 | 2004-01-13 | 2004-02-13 |  | 2004-04-07 | 2004-04-29 |  | 2004-08-25 |  | 2009-12-11 |  | 12/22/2010, 1/25/2010 |  | Land use restricted to non-residential. | Deed recordation noting presence of ACM in the disturbed zone. |  |  |  | Active - CCOC
53031003 | Beverly Hills Ave / San Mateo (Fidelity Trust) | Albuquerque | Bernalillo | No Street Address | T11N, R3E, Sec 12 | 35.1941 | -106.5855 | 2.5 | Solid waste, landfill gases. |  | Fidelity Trust Bank | Shean | 2002-11-18 |  |  |  | 2003-06-26 | [5 empty] | 2003-12-01 |  |  |  |  | 2003-12-12 | 2010-09-08 |  | Closed
53031002 | First Federal Bank @ Digital | Albuquerque | Bernalillo | 4301 The 25 Way NE | T10N, R5E, Sec 13 | 35.1445 | -106.5964 | 1.279 | Chlorinated solvents. |  | First Federal Bank | Bynum | 2002-09-24 |  |  |  | 2002-12-05 | [5 empty] | 2002-12-17 |  |  |  |  | 2002-12-18 |  |  | Closed
53031001 | Casey Luna Ford | Belen | Valencia | 19381 North I-25 Business Loop | T5N, R2E Sec 6 | 34.6879 | -106.7675 | 5.59 | Petroleum hydrocarbons. |  | Casey and Beverly Luna | Muir | 2002-07-25 |  |  | 2009-12-11 | [14 empty] | Closed
53024001 | O'Neal Family Trust/Gateway Subdivision | Carlsbad | Eddy | 1108 West Pierce St. | T21S, R26E, Sec 36 | 32.4364 | -104.24 | 1.33 | Petroleum hydrocarbons. |  | O'Neal Family Trust | Cook | 2002-03-21 |  | 2002-07-05 |  | 2002-08-12 | 2002-12-02 | [6 empty] | 2018-01-31 | [5 empty] | Closed
53023002 | Peru Hill Mill | Deming | Luna | Vacant county land | T23S, R9W, Sec 18 & 19, part of Sec 17 & 20 | 32.3036 | -107.81 | 1479.34 | Metals. | NMD07119986 | City of Deming | Muus | 2002-02-26 |  |  |  | 2003-04-30 | 2003-07-15 |  |  | 2009-02-10 | 2009-02-27 |  | 2010-03-04 |  | Land use restricted to industrial/commercial use. | Former tailings areas have fencing and engineered cap requiring semi-annual inspections and maintenance as needed. Ground water monitoring in 2016 and 2021. | 2010-03-14 |  |  | Active - CCOC
53023001 | L & P Properties | Las Cruces | Doña Ana | 300 N. Archuleta | T23S,R1E, Sec 13 | 32.305 | -106.7958 | 1.27 | Petroleum hydrocarbons. |  | Paul Buldain | Muir | 2001-08-30 | 2001-12-19 | 2002-01-03 |  | 2002-02-13 | 2002-04-04 |  |  |  | 2010-06-04 | 2010-11-30 | [7 empty] | Closed
53022001 | Medite Corp., Las Vegas Div. | Las Vegas | San Miguel | U.S. Highway 85 | T16N, R17E, Sec 6 | 35.6458 | -105.1833 | 78.11 | Petroleum hydrocarbons. |  | Medite Corp. | Bascomb | 2002-04-29 |  |  |  | 2003-10-29 | [5 empty] | 2004-02-17 | [7 empty] | Closed
53021007 | Serna Trucking | Albuquerque | Bernalillo | 480 Sunset Road | T10N, R3E, Sec 19 | 35.0754 | -106.676 | 15 | Petroleum hydrocarbons. |  | Bernalillo County | Sims | 2002-02-07 |  |  |  | 2002-07-26 | [5 empty] | 2002-10-10 |  |  |  |  | 2002-12-18 |  |  | Closed
53021006 | Comet Cleaners @ Skyview | Albuquerque | Bernalillo | 1520 Tramway Boulevard NE | T10N, R4E, Sec 14 | 35.0961 | -106.4965 | 0.25 | Chlorinated solvents. |  | Clean Inc. | Faris | 2002-03-01 |  |  |  | 2003-04-25 | [5 empty] | 2004-01-09 | [7 empty] | Closed
53021005 | Del Norte Gun Club | Sandoval County | Sandoval | Idalia Road @ NM 528 | T13N, R3E, Sec 36 | 35.3069 | -106.5841 | 56 | Lead shot - firing range. |  | Sandoval County | Muus | 2003-10-03 | 2002-04-26 | 2004-08-13 |  | 2003-10-03 | 2003-10-21 |  | 2005-12-06 |  | 2008-12-23 |  | 04/24/2009, 5/26/2009 |  | No development within 25-foot radius of asphalt capped area. | Deed restriction, asphalt cap over affected soils. |  |  |  | Active - CCOC
53021004 | Triple S, Inc. (Kerr McGee Number #6007) | Albuquerque | Bernalillo | 322 Louisiana Boulevard SE | T10N, R4E, Sec 30 | 35.0728 | -106.5686 | 0.3 | Petroleum hydrocarbons. |  | Triple S, Inc. | Mariano | 2001-11-13 |  |  |  | 2002-05-15 | [5 empty] | 2002-07-22 |  |  |  |  | 2005-04-04 |  |  | Closed
53021003 | Ramsey Oil | Grants | Cibola | 210 W. Santa Fe Avenue | T11N, R10W, Sec 25 | 35.1498 | -107.849 | 56 | Petroleum hydrocarbons. |  | BNSF Railway Co. | Cook | 2001-09-28 | 2001-10-22 | 2001-11-14 |  | 2002-01-03 | 17-Jan-02 9-Aug-17 | 2016-09-01 | 2002-01-17 | 2016-09-01 | 2018-01-26 |  | 2018-08-24 |  | land use retricted to non-residential & prohibition of construction of wells into the water bearing zone - administered through NM Office of State Engineer. |  |  |  |  | Active-CCOC
53021002 | Coca Cola Bottling Plant | Albuquerque | Bernalillo | 205 Marquette Avenue NE | T10N, R5E, Sec 13 | 35.0879 | -106.6447 | 3.25 | Petroleum hydrocarbons, chlorinated solvents. |  | Commercial Holding Co. | Bynum | 2001-08-13 |  |  |  | 2001-10-19 | [5 empty] | 2002-03-05 |  |  |  |  | 2002-03-05 |  |  | Closed
53021001 | Sun Country Industries | Albuquerque | Bernalillo | 9421 Coors Road NW | T11N, R3E, Sec 18 | 35.1876 | -106.6618 | 1.76 | Solvents (potential volatile organic compounds). |  | Michelson Family Ltd Prtn. | Mariano | 2001-07-31 |  |  |  | 2003-02-04 | [5 empty] | 2003-11-10 | [7 empty] | Closed
53014001 | BNSF Carlsbad Depot Wye Track Area | Carlsbad | Eddy | 110 East Fox Street | T22S, R27E, Sec 6 | 32.425 | -104.225 | 57 | Petroleum hydrocarbons. |  | BNSF Railway Co | Mariano | 2001-03-14 |  |  |  | 2001-06-07 | [5 empty] | 2004-03-01 | [7 empty] | Closed
53013001 | Union Pacific Railroad Alamogordo Former Tie Treating Facility | Alamogordo | Otero | vacant county land | T16S, R9E, Sec 25 | 32.8964 | -105.9661 | 18.619 | Polycyclic aromatic hydrocarbons (PAHs) in soil and ground water. | NMD986669026 | Union Pacific Railroad Co | Furmall | 2001-05-15 |  |  |  | 2001-10-22 | [7 empty] | 2010-04-05 |  |  |  |  | 2009-01-30 | Closed
53012001 | Sanbusco Market Center | Santa Fe | Santa Fe | 560 Montezuma Avenue | T17N, R9E, Sec 13 | 35.6853 | -105.9467 | 4.7985 | Hydraulic oil. |  | Sanbusco Corp. | Bynum | 2001-06-07 |  |  |  | 2001-07-15 | [5 empty] | 2001-07-23 | [7 empty] | Closed
53011007 | San Miguel Shopping Center | Socorro | Socorro | 913 California Street (3 separate parcels) | T10N, R3E, Sec 19 | 34.0676 | -106.8932 | 2.99 | Petroleum hydrocarbons. |  | David Boggs | Mariano | 2001-06-19 |  |  |  | 2001-10-22 | [5 empty] | 2002-04-02 |  |  |  |  | 2002-04-04 |  |  | Closed
53011006 | G&G Auto | Farmington | San Juan | 701 E. 20th Street | T29N, R13W, Sec 10 | 36.7482 | -108.1969 | 3.26 | Chlorinated solvents and petroleum hydrocarbons. |  | McDonalds Corp. | Faris | 2001-03-05 |  |  |  | 2001-06-07 | [5 empty] | 2001-08-29 |  |  |  |  | 2001-09-04 | 2014-12-05 |  | Closed
53011004 | 997 Old Coors Road | Albuquerque | Bernalillo | 997 Old Coors Road | T10N, R2E, Sec 26 | 35.0696 | -106.6998 | 1.25 | Petroleum hydrocarbons. |  | Dennis Romero | Bynum | 2001-02-15 |  |  |  | 2001-05-16 | [5 empty] | 2002-01-17 |  |  |  |  | 2002-01-17 |  |  | Closed
53011003 | Zuni San Mateo Center | Albuquerque | Bernalillo | 5555 Zuni Road SE | T10N, R3E, Sec 25 | 35.0729 | -106.5832 | 5.75 | Chlorinated hydrocarbons. |  | Zuni San Mateo, LLC | Faris | 2000-10-18 |  |  |  | 2001-01-11 | [5 empty] | 2001-10-18 |  |  |  |  | 2001-10-18 |  |  | Closed
53011001 | McGehee & Assoc. | Gallup | McKinley | Vacant land SE of Lincoln & 11th St | T15N, R18W, Sec 16 | 35.5313 | -108.758 | 5.13 | Petroleum hydrocarbons. |  | McGehee & Assoc. | Bynum | 2000-06-22 |  |  |  | 2000-10-02 | [5 empty] | 2000-11-06 |  |  |  |  | 2000-11-07 |  |  | Closed
53003001 | Hop Canyon/Waldo Mill | Socorro County | Socorro | 1.2 miles south of Magdalena | T2S, R4W, Sec 34, 35 | 34.0929 | -107.2265 | 225 | Metals. | NMD981600455 | Asarco | Muir | 2000-03-20 |  |  |  | 2000-06-29 | [13 empty] | Closed
53001004 | Park Avenue Cleaners | Albuquerque | Bernalillo | 1006 Park Avenue SW | T10N, R3E, Sec 20 | 35.0853 | -106.6594 | 0.16 | Chlorinated solvents. |  | Jonathan Siegel | Bynum | 2000-04-07 |  |  |  | 2000-10-31 | [5 empty] | 2000-12-19 |  |  |  |  | 2000-12-20 |  |  | Closed
53001002 | Nine Mile Hill Landfill | Bernalillo County | Bernalillo | I-40 & Paseo de Vulcan | T10N, R2E, Sec 30 | 35.0735 | -106.7744 | 48 | Solid waste landfill. |  | Bernalillo County | Mariano | 1999-10-20 |  |  |  | 2000-04-27 | [5 empty] | 2002-10-01 | [7 empty] | Closed
53001001 | Proposed Forest Service Facility | Albuquerque, Bernalillo County | Bernalillo | 333 Broadway Boulevard SE | T10N, R3E, Sec 20 | 35.0814 | -106.6468 | 3.3994 | Petroleum hydrocarbons. |  | Aardex Corp. | Novick | 1999-08-12 |  |  |  | 1999-12-08 | [5 empty] | 2000-02-07 |  |  |  |  | 2000-02-07 |  |  | Closed
Total | [6 empty] | 140 | 6440.7736 | [22 empty] | 138